## Sprint Plan
Sprint Plan
Sprint No | Sprint Goal | Sprint Tasks | Start Date | End Date | ScrumMaster | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up | Daily Stand-up |  | Sprint Review
[6 empty] | 1 | 2 | 3 | 4 | 5
Project Initiation | For the Scrum master to lead the team to ensure an effective start of the project making sure that all the tasks are completed on time and within the timeframe so that the team stays on track from the beginning. For the Scrum Team to underntand the project aims and objectives and the project goal in order to start off the project well. For the scrum Team to complete all the Sprint 1 tasks up to the highest standards agreed in the group contract To understand the project including the dataset provided. | Complete Group Project Team Roles Test to be completed by every member To decide on the Aims and Objectives To create the GitHub Repository To decide on the Project requiremenets To decide on the Development Methodology To create Mictrosoft Project schedule To create the Risk Mangement Table To understand the features of the dataset | 07.11.2024 | 08.11.2024 | Justyna | Date: 07.11/2024 | Date: 07.11.2024 | Date: 18.11.2024 | Date: 19.11.2024 | Date: 05.12.2024 |  |  | Date: 08.12.2024
[6 empty] | Meeting Time:12pm | Meeting Time:14:00 and 15:00 | Meeting Time: 11am and 2pm | Meeting Time: 10am | Meeting Time: 11am |  |  | Meeting Time: 12pm
[6 empty] | Discussion of: During our first meeting we have went through the teams contract setting up some ground rules that we all agreed to. We have also created a Trello Board with the first tasks we have to complete and also created a GitHub template where will be uploading all of our files. | Discussion of: We have had our first meeting with proffesor Elmahmudi. We have discuess the the dataset he has provided us with and we have agreed on the first steps of the project which is the research part. In our next meeting we will show the proffessor our findings and discuss the next steps of the project. We then had another meeting to discuss what everyone will be doing for the research. | Discussion of: In todays meeting we have started the work on the Microsoft Project schedule, risk assessment table and decided on our Aims and objectives. We have delivered a small presenation during the lecture where we have showed Kulvinder our progress so far and we have recieved feedback on what we have to focus on more which is the project management side. We have then agreed that for the next and last meeting of the project initiaon we will complete more details aims and objectives, we need to research the cost and salaries for our project and also start individual research for the first part of the individual assigment. | Discussion of: The dataset. The team has met for a three hour meeting where research has been conducted to find out details about the dataset provided by the professor Elmahmudi. The HAM10000 dataset is a skin cancer dataset and the team has done the first small research to find out what the dataset includes. Further research will be made during the sprint 1 to find out more information about the selected dataset. | Discussion of: Cost estimation, finding out what people earn as junior AI engineers to be able to make estimate predictions of cost in our project. We have created more details Aims and Objectives and made big progress with the ms Project schedule. We have also decided on the individual reasearch topics with sub areas that we will focus on for our individual report. |  |  | We have sucessfuly finished the project Inition phase, finalising our project aims and objectives, project schedule and agreeing on the research topics for the team to research. The team is to work on the research next with more tasks to come in sprint 1. Project Inition completed.
Sprint 1 | For the Scrum Master to ensure that each member of the team has a research topic to research in order for every team member to be able to complete the first individual report. For the Scrum Team to research the dataset in more detail, reading information from the journals and research papers. To gather all the data needed for the model building and come up with a plan and pipeline for our model building ready for Sprint 2. | To research the dataset in more detail, to read research pepaers relatred to the dataset to understand the possibilities of what can be achieved using this specific dataset To research the classifications models To research the pre-processing stages For the team to work on their individual research To decide on the best model for our project To be able to define the problem To prepare the data for the model, clean the data, perform data argumations | 09.12.2024 | 05.02.2025 | Justyna | Date: 09.12.2024 | Date: 22.01.2025 | Date: 24.01.2025 | Date: 28.01.2025 | Date: 29.01.2025 |  |  | Date: 05.02.2025
[6 empty] | Meeting Time: 10am | Meeting Time: 10:00 - 15:00 | Meeting Time: 11:00 - 14:00 | Meeting Time: 11:00 - 15:00 | Meeting Time: 10:00-17:00 |  |  | Meeting Time: 10:00-11:00
[6 empty] | Discussion of: Progress on the individual research and the findings. Discussing the finidings on the dataset research and combining the research knowledge. Disussion of the features of the dataset and the labels. | Discussion of: Our first assigment -research reports. We have discuessed our dindings and recommendations and discussed how will we apply our recommendations from our reports into our project to make a better solution to our problem. | Discussion of: Steps and design process of creating our model. We have agreed to use the CNN model to our solution after doing our research in the first report. We have created different diagrams to help us with the design process: CNN modeling steps, Machine Learning Pipeline, Design Thinking Problem Solving and the Pre-processing steps. We have also arranged a meeting with our client to discuss our progress and plans for the solution. | Discussion of: New model design and approach. After meeting with our client we have decided on a new approach where we will have more small models to achieve the best solution. We have also agreed on an additional model which will first diagnose whever the patient has arrived to doctors with a lesion on their skin or normal/problamatic skin. This will be a more relaistic approch from the doctors perspective where they have to first diagnose the skin to decide if its lesion, then whever its cancerous or not and finally what type of cancer or if its a differnt illness. | Discussion of: New dataset. In this meeting we have been working together on gathering data for our first model. The images include images of normal skin, spotty skin, chickenpox disease and more. This dataset will be used for training our mmodel to be able to classify non lesion skin. |  |  | We have finished our first sprint and met all of our goals. We did fall behind with work and Sprint1 did take longer than expected but we will try to make the time up in sprint 2 and 3. We have been able to submit our assigments opn tim, complete a very detailed research on our dataset and gathered the second dataset. We have been able to implement some of our recommendations from the first assigment into our solution which we will work on further in Sprint2. | t
Sprint 2 | For Scrum Master: To work on all 4 models with the team and update group blogs after each meeting. To ensure each member has a criteria to talk about for the (b) part of Element 2 with minimal overlaps. To ensure to have meetings with Ali for feedbacks for the models. For the Scrum Team: To ensure the dataset is clean and balanced after pre-processing to be used for the CNN models. To design and implement the 4 Models using appropriate datasets step by step discussing with Ali and getting feedback after each one. To ensure the quality and testing of the models through evaluation. To stay on schedule and try to complete the models by the end of February, allowing work on the website to begin deploying the model. | To gather normal skin images and an equal number of cancerous (mel, bcc and akiec ) and non-cancerous lesions (nv , bkl, vasc and df) for each class. To pre-process the dataset removing hair, resizing, and performing data augmentation to balance the dataset. To label and encode them to prepare them for modelling and classification. To design 2 Binary Class Classifiers to classify between normal and lesions & cancerous and non-cancerous lesions and 2 Multiclass Classifiers to classify between types of cancer and non-cancerous lesions. To use the right hyperparameters such as learning rate, activation functions, epochs and layers to design the neural network. To document after testing on a test plan. To continue working on Project Management Files and Github. To create a change log to document any changes made to Aims and Objectives. | 06.02.2025 | 20.03.2025 | Aleeza | Date: 06.02.2025 | Date: 07.02.2025 | Date: 08.02.2025 | Date: 10.02.2025 | Date: 11 - 12.02.2025 | Date: 18.02.2025 | Date: 6.03.2025 | Date: 20.03.2025
[6 empty] | Meeting Time: 13:00 - 19:00 | Meeting Time:12:00 - 14:00 and 16:00 - 19:00 | Meeting Time: 9 - 14:00 | Meeting Time:11:30 - 14:00 Meeting with Ali: 1st Model | Meeting Time: 11:00 - 15:00 and 9:00 - 12:30 | Meeting Time:1 - 3 | Meeting Time:10:30 - 12 | Meeting Time:10:00-11:00
[6 empty] | Discussion of: Continue working on the dataset gathering normal skin images, and making sure to store them in folders with 1000 images each for normal skin and lesions.Implementing pre-processing steps such as resizing and using DullRazor Algorithm to remove hair. Blockers: Errors using YOLO for hair removal, difficulty finding normal skin images for dataset | Discussion of: Designing and developing the 1st Model to classify between normal skin and lesions with CNN using test dataset containing 250 images from each folder to get an idea of the performance of the model. After making a few changes to the code using L2 Regularization, Dropout, Early Stopping, and Adjusted class weights, we tested it on our original dataset containing 2000 images in total and got a good performance metrics and confusion metrics with low false positives and negatives like we wanted. Blockers: Training took a long time which led to creating a test dataset to avoid waiting long hours to check the performance. | Discussion of: Testing out different Activation Functions such as Swish, Leaky Relu and Elu and the number of epochs to smoothen the training and validation loss graphs, get a lower false negative and positive. To finalize the model to send it to Ali and get Feedback for Monday's Meeting. | 1st Model's Structure, Performance and Feedback from Ali. He was happy and satisfied with the results we got but gave us feedback to make a few changes to the structure of the model and to compare our model with other pre-trained models such as Resnet 50 and VGG 16. He also suggested removing problematic skin having scars, bruises, bumps and redness from normal skin folder as that could come under lesions and using a dataset with reference/source in case we make a publication for it. After the meeting with Ali, we searched for just normal skin images but we couldn't find many so we decided to take images of our own skin to use it as normal skin after asking Ali. Blockers: Finding normal skin images with a reliable source or reference was challenging. Aleeza was uncomfortable taking skin images due to concerns about their potential public use in the future. | Discussion of: Converting format of normal skin images taken from iPhone 15 and 15 Plus for compatibility with our 1st Model and finalizing the dataset with data augmentation to use for pre-trained models and original model. Comparing VGG 16 and Resnet 50 with the original model with our new dataset to see which one should be used. Sending results of the models to Ali for feedback. | 2nd, 3rd and 4th Model We discussed how we'll pre-process the dataset used for 2nd, 3rd and 4th Models and divided them among us. Diba worked on the 2nd Model to classify between Cancerous and Non-cancerous Lesions, Justyna worked on the 3rd Model to classify cancerous lesions into its subtypes and Aleeza worked on the 4th Model to classify non-cancerous lesions into its subtypes. We decided to give ourselves 2 weeks to work on the model and discuss the results with each other to show our best models to Ali. | 2nd, 3rd and 4th Model Feedback from Ali Before having our meeting with Ali, we had a short discussion on WhatsApp and in-person regarding the results we got for our models and which one we'll choose to show to Ali. Ali was happy with our results and suggested increasing the number of epochs to observe the trend in training and validation loss and accuracy graphs. We also showed him our 3rd presentation for our design stage to let him know about other project management-related things we are working on. He recommended creating a comparison table for the models we used (custom CNN and pre-trained models) for our presentation. | We're finally done with our second sprint, and it was a mix of improvements, challenges and solid progress. One of our main goals for this sprint was to create and test all four of our models and we’re now happy with the results and for them to be deployed Throughout the sprint, we had 2 meetings with our client, Ali. His feedback was really helpful, and we made some improvements to the models based on what he suggested. There was a bit of a delay mid-sprint since we all had to focus on our individual assignment that was due in March. That did set us back a little, but we managed to catch up on everything. By the end of the sprint, we had completed all our test plans for pre-processing and model development. We also worked on our Objective Key Results and have gotten feedback for it, and will continue refining them as we move forward. We’re also keeping up with updating our project management files and making sure everything is well-documented and organized on GitHub. We'll now be moving onto the 3rd Sprint where we'll work on deployment of the models.
Sprint 3 | For Scrum Master: To ensure all models are finalized, deployed on the website, and documented on GitHub. To organize the demo recording and guide the team in preparing the final presentation. For the Scrum Team: To complete model evaluation, integrate the models into the website, update GitHub with final files, record the demo, and finish the group presentation and report. | Finalize and evaluate all 4 models using key performance metrics. Deploy models on the website and test functionality. Update GitHub with final code, documentation, and outputs. Record a demo video showing model predictions on the website. Finalize and rehearse the presentation. Complete and submit all project deliverables. | 21.03.2025 | 03.04.2025 | Diba | Date: 27.03.2025 | Date: 31.03.2025 | Date: 01.04.2025 | Date: 02.04.2025 | Date: 03.04.2025 |  |  | Date: 03.04.2025
[6 empty] | Meeting Time: 10:00 - 17:00 | Meeting Time: 9:00 - 18:00 | Meeting Time: 13:00 - 16:00 | Meeting Time: 10:00 - 14:00 | Meeting Time:10:0 - 13:00 |  |  | Meeting Time:10:00-11:00
[6 empty] | Discussion of: Finalizing all 4 models by reviewing metrics such as accuracy, precision, and confusion matrix. Ensured low false positives/negatives and consistency across runs. Blockers: Occasional overfitting in the cancerous vs non-cancerous model, resolved by tweaking class weights and dropout rate. | Discussion of: Deploying the full pipeline on the website using Streamlit. Set up an interactive interface for image upload, prediction display, and model feedback. Ensured smooth user experience and responsive layout. Blockers: Minor delays due to model file size during deployment, resolved by optimizing weights and caching models. | Discussion of: Updating the GitHub repository with final models, scripts, demo images, and README. Verified code clarity, added instructions for usage. | Discussion of: Recording the project demo video showing end-to-end model performance via the website. Drafting and polishing the group presentation for submission. Blockers: Audio syncing issues in the demo video, resolved with re-recording. | Discussion of: Final review and submission of all deliverables including presentation slides, GitHub updates, and video. Each member shared reflections and task completion confirmation. |  |  | We’ve officially wrapped up Sprint 3, and it marked the final phase of our project. The main goal for this sprint was to finalize the four models, deploy them using Streamlit, and complete all required deliverables such as the GitHub update, demo recording, and presentation. One of our biggest accomplishments this sprint was successfully deploying the models on a fully functional website. The Streamlit interface allowed for easy interaction, and we made sure everything—from uploading an image to viewing predictions—worked smoothly. We also updated our GitHub with the final code, structured documentation, and demo media. The repository now clearly reflects our project pipeline and outcomes, and it's ready for public viewing. On top of that, we recorded a full demo and completed our group presentation, assigning clear speaking parts to each team member. There were some small blockers with deployment and syncing edits on GitHub, but we managed to solve them quickly as a team. Overall, this sprint was smooth and highly productive. We're now ready for submission and looking forward to presenting our work.
Scrum Closure | For Scrum Master: To ensure all models, project management files, diagrams, presentation and demo plan are finalized and ready to be submitted by Sunday.To create a checklist of every that needs to be included in the presentation to ensure smooth delivery. To divde presentation slides among team members to practice. To ensure everything is submitted before deadline. For the Scrum Team: Collaborate effectively to ensure all tasks are completed before the submission deadline. Prioritise and fulfill all assignments provided by the Scrum Master to ensure the successful delivery of the project. Ensure the demo plan is fully prepared, clearly articulated, and audible for presentation. | To complete the presentation, finalise all diagrams and project management documentation. Upload all relevant files to GitHub and verify completion using a checklist. Ensure all deliverables are submitted on the Group Blog as the final step. | 04.04.2025 | 06.04.2025 | Justyna | Date: 04.04.2025 | Date: 06.04.2025 | Date: | Date: | Date: |  |  | Date: 06.04.2025
[6 empty] | Meeting Time:9:00 - 13:100 | Meeting Time:11:00 - 12:30 | Meeting Time: | Meeting Time: | Meeting Time: |  |  | Meeting Time:12:30 - 13:00
[6 empty] | Discussion of: Completing and finalising all project management files, including the Microsoft Project plan, Sprint Plan, and Presentation. Used a checklist to double-check that all necessary files are included in both the presentation and the GitHub repository. Preparing a resource file outlining the platforms and tools used, such as Streamlit, Colab Pro, and others. Finalising the project cost estimation slide with the total hours contributed by each team member. Dividing the presentation slides among team members and practicing in advance to ensure smooth delivery during the final presentation. Blockers: Slight issues with Microsft Project, but were solved while working on it. | Discussion of: Making sure the presentation runs smoothly with clear transitions and all images properly attached and visible. Coordinating with team members to ensure everything that needs to be submitted is completed, finalized, and ready.Submitting all required files on the Group Blog in preparation before the deadline for the Final Presentation on Tuesday. | [5 empty] | We have completed the final sprint for our 2nd year final project. Our main focus during this sprint was to ensure that everything was completed, finalised, and thoroughly checked as a group before submission to the Group Blog and for our Final Presentation on Tuesday. We used a detailed checklist and referred back to notes from our lectures to make sure all required files were included. Our GitHub repository now contains all essential files, including model versions, diagrams for model stages, diagrams on multidisciplinary issues, and project management files such as the Microsoft Project plan, Sprint Plan, Test Plans for the final models, and our Team Contract. Throughout this last week, we spent time to refining our presentation while continuing to work on technical tasks. We ensured the presentation included clear visuals and a well-prepared, audible demo plan to explain our models and the webpage we built using Streamlit. Overall, it was a great experience working on this project. We learned a lot, explored new tools and concepts, and successfully tackled several challenges together as a team.