## Sheet1
Risk Assessment ​
Risk​ | Category | Description​ | Affects​ | Strategy​ | Potential Indicator | Probability | Impact
Team Member Absence | People | Team members may not be available because of illness or unexpected events. | Project Progress | Ensure open communication within the team, keeping everyone informed about any illness or absences. Having a backup plan in place which will help distribute responsibilities to other team members such as the scrum master. | Signs of illness, missed lectures, delays in task completion, and reduced productivity. | Moderate - High | Significant
Human error | People - internal | Miscommunication or mistakes | Project, team members | Enure to log discussions for refrence on group blogs and private chats, use test plans etc to spot mistakes easier | Missuderstaning, uncomplete work, not working models etc. | Low - Moderate | Low
Stakeholder Misalignment | People - external | Misunderstanding or mismatched expectations between the team and the client | Project Scope, Delivery | Schedule regular meetings and feedback loops with the client to align goals. | Conflicting requirements or changes late in the project. | Moderate | Significant
Wrong Time Estimations | People - internal | Underestimating the time required for tasks can result in project delays. | Project Timeline | Break tasks into smaller, manageable parts with realistic timelines to avoid underestimating time requirements. Regularly review progress and adjust timelines as needed to stay on track and address any delays. | Missed deadlines Increased amount of time to complete a task (longer than expected) | Moderate - High | Catastrophic
Feedback Ignored or Mismanaged | People / Process | Feedback from the lecturer or the client might be overlooked or poorly implemented. | Model Improvement, Stakeholder Satisfaction | Track feedback systematically and prioritize fixes or adjustments. | Repeated feedback with no visible action. | Moderate | Moderate
Over-reliance on Accuracy Metric | Technical | Focusing only on accuracy may hide other issues like false negatives, especially dangerous in medical diagnosis. | Model Evaluation | Use a variety of metrics like precision, recall, F1-score, and ROC-AUC. | High accuracy but poor recall or precision values. | Moderate | Serious
Data Quality Issues | Technical | Inaccurate, incomplete, or noisy data can severely impact the training process, leading to a model that fails to generalize well. | Model accuracy, training time | Implement thorough data validation, data cleaning techniques, and augment data to improve quality. | Decreased model performance and high training loss | Low | Catastrophic
Limitations and Technical Issues with Colab | Technical | If the subscription isn’t paid for, you can lose access to longer GPU runtimes which is required for a large dataset and long codes. Shift from GPU to CPU could cause glitches | Model, Project Progress | Invest in Google Colab Pro to have unlimited access to GPU for our tasks | Change of GPU to CPU - taking longer for codes to run. | High | Catastrophic
Choosing the wrong model for diagnosis | Technical | An incorrect model may fail to identify cancer cases (missed diagnoses) or incorrectly classify healthy cases as cancer (false negatives and false positives) which could lead to harmful outcomes. | Accuracy and reliability of Model | Explore and research different models/algorithms thoroughly before selection, and use techniques like cross-validation to test model reliability. | Getting a poor performance metrics during testingphases, unpredictable performance when applied to new or unseen data. | Low - Moderate | Serious
Model Overfitting and Underfitting | Technical | The model may learn to perform well on training data but fail on unseen data or might be too simple and can't capture the underlying relationships and patterns. | Model Generalization | Use data augmentation (e.g., rotation, flipping) to diversify training data. Apply transfer learning with pre-trained models (e.g., VGG, ResNet) and fine-tune them. Implement CNNs with convolutional for feature extraction. Normalise input data for consistent training. | The model may perform well on the training data but show lower accuracy on validation or test data. | Moderate - High | Catastrophic
Data Bias | Ethical | The dataset may not represent diverse skin tones or age groups leading to biased predictions. | Model Fairness and Accuracy | Implementing transfer learning with a pre-trained model that has been trained on a more diverse dataset including different skin tones to enhance model generalization. Normalize or pre-process to standardize texture features acrosss all skin type helping the model learn relevant characteristics that are common to various skin tones. | Reduced model performance for certain demographic groups | Moderate - High | Serious
Data Privacy | Ethical | Team members creating own dataset and ensuring it is stored safely and with consent to use | Team members privacy | Signing an image consent form | Leaked images, data breach | Moderate - High | Catastrophic
Weather Conditions | External | Bad weather causing cancelled lectures or team members unable to arrive to team meetings due to weather conditions | Project Progress | Ensure to have a backup plan such as online meetings or availability to reschedule meetings | Snow, Thunder etc. | Low | Low
Budget Constraints | Financial | Limited funds may restrict access to premium tools | Project Scope, Model Performance | Prioritize essential resources and use free alternatives where possible. | Unable to purchase necessary services like Colab Pro, limited dataset access. | High | Serious